RolplayPro

Unified Dashboard

Phase 1 Roadmap

Developer Kickoff Meeting

Version 3.0  |  March 2026

Author: Diego Merigo

Delivery target: 5 weeks to production-ready first release

Stack: React / Next.js + Shadcn UI  |  Architecture: Standalone dashboard app

Confidential — For Internal Use Only

Table of Contents

1. Project Framing

2. Confirmed Realities and Constraints

3. Data Availability Classification

4. Launch Scope Definition

5. Proposed Dashboard Structure

6. KPI Framework (Tier-Classified)

7. Five-Week Roadmap

8. Sprint Operating Model

9. Developer-Ready Task Breakdown

10. Open Questions and Confirmed Assumptions

Appendix A — Design Reference Notes

Appendix B — Component Inventory

# 1. Project Framing

## 1.1 What this is

The RolplayPro Unified Dashboard is a single analytics interface that gives clients real-time visibility into how their teams progress across all five core solutions: LMS, Master Coach, Practice Simulator, Expert Certification, and Second Brain.

It is one global dashboard with intelligent filtering. The user sees platform-wide metrics first, then filters by one or more solutions to drill into specific areas. Every solution-specific view follows the same base structure: KPI summary cards, main chart, and detail table.

## 1.2 What has changed since v2

Developer input confirmed four realities that fundamentally reshape the project:

- No analytics foundation exists. The current platforms (rolplay.pro, coach) do not have analytics infrastructure. There are no aggregation endpoints, no analytics database, and no computed metrics layer. Everything must be built from scratch.

- No user activity tracking exists. User-level activity data (session timestamps, interaction logs, page views, query histories) is not being collected. The current privacy policy explicitly states this. Introducing activity tracking requires a privacy policy update and potentially legal review.

- Standalone architecture confirmed. The developers recommend building the dashboard as a separate application, independent from the main platforms. This allows embedding when needed and avoids coupling to the legacy codebase.

- Platform transition underway. Rolplay2 is the planned successor to coach. The dashboard should be built to align with Rolplay2’s direction, not deeply coupled to the current coach platform.

## 1.3 Why it still matters

The strategic rationale remains unchanged. Clients need visible ROI. Sales demos need a data story. The platform must feel like a unified ecosystem, not disconnected tools. What changes is the execution approach: the first release must be built on data that is actually available today, not on data we wish existed.

## 1.4 The honest scope reframe

Key constraint Roughly half of the KPIs in the previous roadmap depend on user-level activity data that does not exist and cannot be introduced without a privacy/policy decision. The first release must be planned around what the transactional databases already contain, supplemented by backend aggregation that can be computed from existing records. Activity-dependent metrics are deferred until the privacy decision is made and tracking is implemented.

## 1.5 Product principle (unchanged)

- One unified global dashboard, not five disconnected views

- Filterable by one or multiple solutions

- Interactive date filters, date-range comparisons, and drill-down where data permits

- Each solution view follows the same base structure: KPI cards, main chart, detail table

- Only break that structure if a specific solution genuinely requires it

# 2. Confirmed Realities and Constraints

## 2.1 Platform landscape

| Item | Confirmed status |
| --- | --- |
| Current platforms | Two exist today: rolplay.pro and coach. All current functionality is built on these two. |
| Rolplay2 | Upcoming platform intended to replace coach with a streamlined foundation. Long-term direction. |
| rolplay.pro | Acceptable for demos but not practical for multi-client production use. |
| Dashboard architecture | Standalone application (confirmed by developers). Separate from main apps, embeddable when needed. |

## 2.2 Data infrastructure

| Item | Confirmed status |
| --- | --- |
| Analytics backend | Does not exist. No aggregation endpoints, no analytics database, no computed metrics layer. |
| API endpoints for metrics | Do not exist. Must be designed and built as part of this project. |
| User activity tracking | Not collected. Privacy policy explicitly states this. Introducing it requires policy change + possible legal review. |
| Transactional data | Exists in current databases: user records, module/course assignments, evaluation scores, completion records, use case configurations. Extent and schema need to be audited in Week 1. |

## 2.3 Team capacity

| Item | Confirmed status |
| --- | --- |
| Lead developer | One developer leading both backend and frontend work for 5 weeks. |
| Support developers | Two developers available occasionally for well-scoped tasks. |
| Product owner | Diego — defines scope, priorities, reviews deliverables weekly. |

## 2.4 What this means for the first release

The first release must be built on three layers of data availability, with clear separation between what ships at launch and what requires additional decisions or infrastructure:

- Launch with transactional data. Use what already exists in the database: user counts, module completions, certification scores, assignment records. These can be aggregated into meaningful KPIs without new tracking.

- Build backend aggregation. Create API endpoints that compute metrics from existing transactional records. This is engineering work within the 5-week scope.

- Defer activity-dependent metrics. Any metric that requires session-level timestamps, interaction logs, or behavioral tracking cannot ship until the privacy decision is made, the policy is updated, and tracking is implemented. These are Phase 2.

# 3. Data Availability Classification

Every metric in this project is classified into one of three tiers based on what data is actually available or buildable within the 5-week timeline.

| Tier | Label | Definition |
| --- | --- | --- |
| Tier A | Available now | Derivable from existing transactional databases. Requires API endpoint + frontend. No new tracking. No privacy changes. |
| Tier B | Requires backend build | Requires new aggregation logic, computed fields, or minor schema additions built on top of existing transactional data. Engineering work within scope. No privacy changes. |
| Tier C | Requires activity tracking + privacy decision | Requires new user-level activity instrumentation (session timestamps, interaction logs, query histories). Cannot be built until privacy policy is updated and tracking infrastructure is implemented. Deferred to Phase 2. |

## 3.1 What likely exists in transactional databases (Tier A candidates)

These records are assumed to exist because they are functionally necessary for the current platforms to operate. The exact schema must be audited in Week 1.

- User accounts: user ID, name, email, creation date, assigned organization/tenant

- LMS module/course assignments: which users are assigned to which modules

- LMS completion records: which users completed which modules, completion date

- LMS quiz results: quiz scores per attempt (if quizzes are a functional feature today)

- Expert Certification evaluation records: score, pass/fail status, evaluation date, rubric results

- Use case configurations: which solutions/scenarios are configured per client

- Second Brain: knowledge base document inventory (files uploaded, topics indexed)

## 3.2 What likely does not exist (Tier C candidates)

These data points are explicitly not being collected per the developer confirmation and privacy policy:

- Session start/end timestamps (when a user opened/closed any solution)

- Interaction counts (how many questions asked to Master Coach, how many queries to Second Brain)

- Session duration (how long a user spent in any solution)

- Last active date per user

- Practice Simulator individual session scores with timestamps

- Second Brain query logs (what was searched, when, response quality)

- Page views, click events, navigation patterns

## 3.3 The gray zone (Tier B candidates)

Some metrics can be computed from transactional data with new aggregation logic, even without activity tracking. Examples:

- Total certified users = count of users with at least one passing evaluation record

- Pass rate = passing evaluations / total evaluations

- LMS completion rate = completed assignments / total assignments

- Average certification score = mean of evaluation score records

These require building aggregation queries and API endpoints but do not require new event tracking or privacy changes.

Week 1 critical action The lead developer must audit the actual database schema in Week 1 to confirm which records exist, their structure, and their completeness. This audit determines which Tier A and Tier B metrics are truly feasible. Do not commit to specific KPIs until the audit is complete.

# 4. Launch Scope Definition

## 4.1 Tier 1 — Mandatory for launch (Tier A + Tier B metrics only)

The first release ships with metrics that are computable from existing transactional data plus backend aggregation. No metric that depends on user activity tracking is included in launch scope.

| # | Feature | Rationale |
| --- | --- | --- |
| 1 | Unified global overview with KPI cards | Must communicate value at first glance. Cards show only Tier A/B metrics. |
| 2 | Solution filter (multi-select for 5 core solutions) | Core differentiator. Filters adjust all displayed metrics. |
| 3 | Date range selector (7d, 30d, 90d, custom) | Temporal control — date ranges apply to transactional record timestamps (creation/completion dates). |
| 4 | Comparison period with trend indicators | Proves improvement over time using transactional record date fields. |
| 5 | KPI summary cards with trend % and sparkline | Scannable top-level metrics. Only Tier A/B metrics displayed. |
| 6 | Primary chart per view | Activity/completion trends using transactional record dates as the time axis. |
| 7 | Solution-specific views (all 5) following unified layout | Cards + chart + table structure consistent across all views. |
| 8 | Data tables with sortable columns | Managers need user-level and module/scenario-level breakdowns. |
| 9 | Empty states for all views | Clients with partial deployments must never see a broken screen. |
| 10 | CSV export of active table view | Minimum export for offline reporting. |
| 11 | Responsive layout (desktop + tablet) | Clients access from multiple devices. |
| 12 | Loading states and error handling | Production-grade quality. |
| 13 | Backend API: aggregation endpoints for all launch metrics | No analytics backend exists today — this must be built. |
| 14 | Database schema audit (Week 1) | Confirms exactly which data exists and its structure. |
| 15 | Standalone app scaffolding + auth integration | Confirmed architectural direction. Auth mechanism to be determined in Week 1. |

## 4.2 Tier 2 — Enhancements if time allows (still Tier A/B data only)

| # | Feature | Rationale |
| --- | --- | --- |
| 16 | PDF export of overview page | Professional executive reporting. |
| 17 | Learning funnel visualization | Visually reinforces ecosystem narrative using assignment/completion/certification counts. |
| 18 | Top/bottom performers by certification score | Quick outlier identification. |

## 4.3 Tier 3 — Post-launch (requires decisions or infrastructure)

| # | Feature | Blocker | Target |
| --- | --- | --- | --- |
| 19 | Session-based engagement metrics (duration, frequency, last active) | Privacy decision + activity tracking | Phase 2 |
| 20 | Master Coach interaction depth (questions asked, topics) | Activity tracking | Phase 2 |
| 21 | Second Brain query analytics (search volume, topics, satisfaction) | Activity tracking | Phase 2 |
| 22 | Simulator per-session score trends and improvement rate | Session-level score tracking | Phase 2 |
| 23 | Cross-solution adoption rate (users who used 2+ solutions) | Session/activity tracking per solution | Phase 2 |
| 24 | AI-powered insight summaries | Analytics maturity + AI scope | Phase 2 |
| 25 | Custom report builder / saved views | Product complexity | Phase 2 |
| 26 | Role-based permissions | Product complexity | Phase 2 |
| 27 | Scheduled email reports | Infrastructure | Phase 3 |

Scope principle It is better to ship a dashboard with 15 accurate, trustworthy metrics than one with 30 metrics where half show incomplete or misleading data. The first release builds credibility. Phase 2 expands depth.

# 5. Proposed Dashboard Structure

## 5.1 Top-level layout (unchanged)

Sidebar + main content area. Sidebar navigates between global overview and each solution. Main content always follows: toolbar (date range, comparison, solution filter) then KPI cards, then chart, then table.

Sidebar navigation

- Global Overview (default landing)

- LMS

- Master Coach

- Practice Simulator

- Expert Certification

- Second Brain

- Export

- Settings

## 5.2 Filtering logic

Solution filter: Multi-select on Global Overview. Auto-set and disabled on solution-specific views.

Date range: Applies globally. Uses transactional record date fields (creation date, completion date, evaluation date) as the time axis. Presets: 7d, 30d, 90d, custom. Default: Last 30 days.

Comparison period: Auto-calculated: same duration, immediately prior. Shown as trend % on cards. Optionally as dashed overlay on charts.

Behavioral rule: Changing any filter updates all cards, charts, and tables simultaneously.

## 5.3 Metric groups per view (adjusted for data availability)

All metrics shown below are Tier A or Tier B. Tier C metrics are excluded from launch.

| View | Summary cards | Primary chart | Table |
| --- | --- | --- | --- |
| Global Overview | Total users, Total enrolled (LMS), Total certified, Avg cert score | Certifications over time (line) | User summary (name, LMS %, cert score, cert status) |
| LMS | Enrolled users, Completion rate, Avg quiz score, Modules completed | Module completions over time (line) | Module breakdown (name, enrolled, completed, avg score) |
| Master Coach | Configured use cases, Users assigned, Knowledge base docs | Use case deployment over time (bar) | Use case list (name, status, assigned users) |
| Simulator | Configured scenarios, Users assigned, Total practice sessions* | Scenario deployment (bar) | Scenario list (name, assigned users, status) |
| Certification | Candidates evaluated, Pass rate, Avg score, Pending certs | Pass/fail over time (stacked bar) | Results table (user, cert, score, status, date) |
| Second Brain | Knowledge base docs, File types indexed, Total file size | Document uploads over time (bar) | Document inventory (name, type, date added, size) |

* Practice sessions count is only feasible if session completion records exist in the transactional database. To be confirmed in Week 1 audit.

## 5.4 Drill-down logic (Phase 1)

- Summary cards: Display-only. No click drill-down.

- Chart hover: Tooltip with exact value + comparison value.

- Table row click: Detail slide-over panel showing user-level or item-level breakdown (only with data available from transactional records).

- Table sorting: All columns sortable.

- Table search: Text filter on name column.

## 5.5 Export logic

| Export type | Scope | Format | Priority |
| --- | --- | --- | --- |
| Active table view | Current view + active filters | CSV | Mandatory |
| Overview snapshot | Current view as rendered | PDF | Enhancement |
| Raw data export | All records for date range | CSV | Phase 2 |

## 5.6 Empty and no-data states

| State | Behavior |
| --- | --- |
| No data at all | Illustration + message: “No activity recorded yet for [Solution].” Link to setup guide if applicable. |
| Partial data | Cards with data render normally. Cards without show “—” with tooltip. |
| Loading | Skeleton loaders (Shadcn pattern). No full-page spinner. |
| API error | Error component with retry button. No silent failures. |
| Solution not configured | Clear message: “This solution is not yet configured for your organization.” |

# 6. KPI Framework (Tier-Classified)

## 6.0 Design principles

- Every launch metric must be computable from confirmed transactional data. No assumptions about activity tracking.

- Every metric includes comparison delta (trend %) using transactional record dates.

- Metrics flagged as data-dependent are contingent on the Week 1 database audit confirming the required records exist.

- Tier C metrics are documented for Phase 2 planning but excluded from the first release.

| Tier A = Available now | Tier B = Backend build required | Tier C = Activity tracking + privacy |
| --- | --- | --- |

## 6.1 Global / Cross-platform metrics

| Metric | Definition | Why it matters | Display | Data tier |
| --- | --- | --- | --- | --- |
| Total registered users | Count of user accounts in the platform | Reach indicator | Card + sparkline | Tier A |
| Total LMS enrolled | Users assigned to at least 1 module | Learning layer reach | Card | Tier A |
| Total certified users | Users with at least 1 passing evaluation | Readiness indicator | Card | Tier A |
| Avg certification score | Mean score across all evaluations | Quality outcome | Card | Tier B (aggregation) |
| Certifications over time | Evaluation completions by date | Progress trend | Line chart | Tier B (aggregation) |
| User summary table | User, LMS %, cert score, cert status | Operational view | Data table | Tier B (join query) |
| Cross-solution adoption | % users active in 2+ solutions | Ecosystem value proof | Card | Tier C (deferred) |
| Total active users | Users with at least 1 session in period | Engagement health | Card | Tier C (deferred) |
| Total sessions | Sum of sessions across solutions | Volume indicator | Card | Tier C (deferred) |

## 6.2 LMS metrics

| Metric | Definition | Why it matters | Display | Data tier |
| --- | --- | --- | --- | --- |
| Enrolled users | Users assigned to at least 1 module | Content layer reach | Card | Tier A |
| Completion rate | Completed / total assignments | LMS effectiveness | Card (%) | Tier B (aggregation) |
| Avg quiz score | Mean score across quizzes taken | Comprehension quality | Card | Tier B (aggregation) |
| Modules completed | Count of completion records | Learning volume | Card | Tier A |
| Completions over time | Completion records by date | Learning momentum | Line chart | Tier B (aggregation) |
| Module breakdown | Module name, enrolled, completed, avg score | Identifies weak content | Data table | Tier B (aggregation) |
| Time spent learning | Hours in LMS content per user | Effort indicator | Card | Tier C (deferred) |

## 6.3 Master Coach metrics

| Metric | Definition | Why it matters | Display | Data tier |
| --- | --- | --- | --- | --- |
| Configured use cases | Count of coach use cases set up | Deployment breadth | Card | Tier A |
| Assigned users | Users assigned to coach interactions | Reach indicator | Card | Tier A |
| Knowledge base docs | Documents in the coach knowledge base | Content coverage | Card | Tier A |
| Use case list | Name, status, assigned user count | Operational view | Data table | Tier A |
| Active users | Users with at least 1 session | Adoption depth | Card | Tier C (deferred) |
| Total sessions | Coaching conversations started | Engagement volume | Card | Tier C (deferred) |
| Avg session duration | Mean time per session | Depth of engagement | Card | Tier C (deferred) |
| Questions asked | Total questions submitted | Interaction intensity | Card | Tier C (deferred) |
| Top topics | Most queried knowledge areas | Knowledge gap signal | Table | Tier C (deferred) |

Master Coach — reduced launch scope Without activity tracking, Master Coach metrics are limited to configuration and assignment data. The view will show what is set up and who has access, but not how it is being used. This is a known limitation for v1. Activity-based engagement metrics are a priority for Phase 2 once the privacy decision is made.

## 6.4 Practice Simulator metrics

| Metric | Definition | Why it matters | Display | Data tier |
| --- | --- | --- | --- | --- |
| Configured scenarios | Count of simulation scenarios set up | Deployment breadth | Card | Tier A |
| Assigned users | Users assigned to simulation practice | Reach indicator | Card | Tier A |
| Scenario list | Scenario name, status, assigned users | Operational view | Data table | Tier A |
| Practice sessions* | Total completed simulation records | Volume indicator | Card | Tier B (audit-dep.) |
| Active users | Users with at least 1 session | Practice adoption | Card | Tier C (deferred) |
| Avg performance score | Mean score per simulation | Execution quality | Card | Tier C (deferred) |
| Improvement rate | Score change from first to latest | Growth proof | Card | Tier C (deferred) |
| Score trend | Avg score over time | Quality trend | Line chart | Tier C (deferred) |

* Practice sessions count depends on whether session completion records are stored in the transactional DB. Week 1 audit will confirm.

## 6.5 Expert Certification metrics

| Metric | Definition | Why it matters | Display | Data tier |
| --- | --- | --- | --- | --- |
| Candidates evaluated | Users with at least 1 evaluation | Validation reach | Card | Tier A |
| Pass rate | Passing evaluations / total | Readiness rate | Card (%) | Tier B (aggregation) |
| Avg score | Mean evaluation score | Quality distribution | Card | Tier B (aggregation) |
| Pending certifications | Assigned but not yet evaluated | Action item for managers | Card (alert) | Tier B (delta query) |
| Pass/fail over time | Evaluations by date, pass vs fail | Readiness trend | Stacked bar | Tier B (aggregation) |
| Results table | User, cert name, score, status, date, attempts | Detailed record | Data table | Tier A |

Expert Certification — strongest launch view Certification has the richest transactional data because evaluation scores, pass/fail outcomes, and dates are stored as part of the core platform workflow. This will be the most complete and compelling solution view at launch.

## 6.6 Second Brain metrics

| Metric | Definition | Why it matters | Display | Data tier |
| --- | --- | --- | --- | --- |
| Knowledge base docs | Total documents in the knowledge base | Content coverage | Card | Tier A |
| File types indexed | Breakdown by file format (pptx, xlsx, docx, pdf) | Content diversity | Card | Tier A |
| Document inventory | Document name, type, date added, size | Operational view | Data table | Tier A |
| Total queries | Count of user queries | Usage volume | Card | Tier C (deferred) |
| Avg queries per user | Queries / active users | Engagement depth | Card | Tier C (deferred) |
| Top searched topics | Most queried knowledge areas | Demand signal | Table | Tier C (deferred) |
| Response satisfaction | % rated positively | Quality indicator | Card | Tier C (deferred) |

Second Brain — reduced launch scope Similar to Master Coach, Second Brain metrics at launch are limited to what is configured (knowledge base inventory), not how it is being used. Query analytics are Tier C and require activity tracking. The v1 view will serve as a content management dashboard for the knowledge base.

# 7. Five-Week Roadmap

## Week 1 — Database Audit, Architecture, and Foundation

Objective: Audit the actual database schema across both platforms to determine exactly what transactional data exists. Make the architecture and auth decisions. Set up the standalone app and deliver a skeleton Global Overview.

| Area | Deliverable |
| --- | --- |
| Database audit | Complete schema audit: which tables exist, what fields, what date columns, what is reliably populated across both platforms (rolplay.pro, coach) |
| Data tier confirmation | Classify every planned metric into Tier A (confirmed available), Tier B (buildable), or Tier C (deferred). Lock the final KPI list for launch. |
| API design | Document API contract: endpoints, schemas, query params. Designed around confirmed data. |
| Architecture | Standalone Next.js app initialized. Auth integration approach decided. |
| Components | SummaryCard, ChartWrapper, SkeletonLoader built and tested. |
| Global Overview | Skeleton page with placeholder cards and structure. Connected to at least 1 real endpoint if possible. |

Decisions to lock in Week 1

- Final KPI list for launch (based on audit, not assumptions)

- Auth mechanism: reuse existing auth, new JWT, or SSO

- Multi-tenancy scoping approach

- Chart library (Recharts recommended)

- Database connection strategy: direct queries vs. analytics DB replica

- Which platform’s database is the primary source (coach, rolplay.pro, or Rolplay2)

Key risks

- Risk: Database audit reveals less data than expected. Mitigation: if critical records are missing, reassess launch scope immediately rather than building around incomplete data.

- Risk: Auth integration is complex between standalone app and existing platforms. Mitigation: stub auth for Week 1, finalize by Week 3.

- Risk: Two databases (rolplay.pro and coach) may have different schemas. Mitigation: choose one primary source for v1; do not try to merge both.

Developer review (end of Week 1)

- Review database audit results together

- Confirm the final launch KPI list (Tier A and Tier B only)

- Walk through the app skeleton and Global Overview page

- Confirm the API contract document

## Week 2 — Backend API + Solution Views

Objective: Build backend aggregation endpoints for all confirmed launch metrics. Implement all 5 solution views using the unified layout pattern. Implement date range and comparison logic.

| Area | Deliverable |
| --- | --- |
| Backend API | Aggregation endpoints for Global, LMS, Certification (highest data density first). Then Coach, Simulator, Second Brain. |
| Date logic | Date range filtering and comparison period calculation on all endpoints. |
| Solution views | All 5 solution views built: cards + chart + table, using the unified layout pattern. |
| Filtering | Date range selector (presets + custom), comparison period, solution multi-select on Global Overview. |
| Components | DataTable (sortable, searchable, paginated), chart variants (line, bar, stacked bar, area). |

Priority order for backend endpoints

- Expert Certification — richest transactional data, most complete view

- LMS — strong transactional records (enrollments, completions, quiz scores)

- Global Overview — aggregates from the above + user counts

- Master Coach — configuration/assignment data (limited but functional)

- Practice Simulator — configuration/assignment data (limited, session count TBD)

- Second Brain — knowledge base inventory (document metadata only)

Key risks

- Risk: 5 views + backend endpoints in one week is aggressive. Mitigation: Coach, Simulator, and Second Brain views are simpler (fewer metrics, Tier A configuration data only). Certification and LMS are the complex ones — prioritize those.

- Risk: Aggregation queries on transactional databases are slow. Mitigation: add database indexes. Consider materialized views for complex aggregations.

Developer review (end of Week 2)

- Navigate all 6 views end to end

- Test date range changes: confirm all components update simultaneously

- Review backend response payloads for accuracy and performance

## Week 3 — Drill-down, Export, Data Integration

Objective: Add drill-down panel, CSV export, connect all views to real data, harden error handling. Complete any remaining backend endpoints.

| Area | Deliverable |
| --- | --- |
| Drill-down | User/item detail slide-over panel. Content depends on data available per solution. |
| Export | CSV export of active table view, respecting all filters. |
| Data integration | All views connected to real backend APIs. No mock data remaining. |
| Error handling | API error states, timeout handling, retry logic across all views. |
| Backend (final) | Complete any remaining endpoints. Auth integration finalized. |

Key risks

- Risk: Real data reveals edge cases: null values, missing dates, inconsistent records. Budget at least 1 day for data normalization.

- Risk: User-level data for the drill-down panel may be incomplete for solutions with only Tier A (configuration) data. In those cases, the drill-down shows a reduced set of fields.

Developer review (end of Week 3)

- Export CSV and verify data integrity

- Open drill-down panel from every solution table

- Confirm all views run on real data

## Week 4 — Empty States, Polish, QA Start

Objective: Implement all empty/loading/error states. Visual polish pass. Responsive testing. Begin QA.

| Area | Deliverable |
| --- | --- |
| Empty states | All views handle: no data, partial data, solution not configured, loading, error. |
| Polish | Sparklines on cards, chart tooltips, responsive adjustments, typography/spacing. |
| Responsive | Desktop + tablet viewport testing. |
| QA begin | Systematic testing of all views, filters, exports, edge cases. |
| Backend | Query performance optimization. Index tuning for large datasets. |

Developer review (end of Week 4)

- Test every empty state scenario

- Test on tablet viewport

- Full client-simulation walkthrough

## Week 5 — QA, Deployment, Launch

Objective: Feature freeze. Complete QA. Deploy to staging. Internal demo. Production launch. Tier 2 enhancements only if time remains.

| Area | Deliverable |
| --- | --- |
| QA | Full regression: all views, filters, exports, empty states, edge cases, cross-browser. |
| Integration | Auth flow end-to-end. Multi-tenant data isolation verification. |
| Performance | Lazy loading, bundle size check, query performance under load. |
| Deployment | Staging deploy, smoke test, production deployment pipeline. |
| Launch | Internal demo, known issues log, v1 release notes. |
| Tier 2 (if time) | PDF export, learning funnel visualization, top/bottom performers. |

Developer review (end of Week 5)

- Full walkthrough as if demo-ing to a client

- Staging deployment and smoke test

- Sign-off: launch blockers vs. known limitations

# 8. Sprint Operating Model

## 8.1 Weekly cadence

| Ceremony | When | Duration | Purpose |
| --- | --- | --- | --- |
| Sprint kickoff | Monday AM | 30 min | Review objectives, confirm tasks, surface blockers |
| Midweek checkpoint | Wednesday PM | 15 min | Progress check, unblock, adjust scope if needed |
| End-of-week review | Friday PM | 45 min | Demo working software, review criteria, decide what ships |

## 8.2 Communication protocol

- Async updates: Lead developer posts daily Done / Doing / Blocked.

- Blocker escalation: Anything unresolved in 4 hours escalated immediately.

- Scope changes: All scope changes go through Diego. Developer never self-adds scope.

- Support developers: Diego assigns specific, well-scoped tasks. No ambiguous handoffs.

## 8.3 Expected artifacts per week

| Week | Required artifact |
| --- | --- |
| Week 1 | Database audit report, data tier classification, API contract, architecture decision record, app skeleton |
| Week 2 | All 6 views navigable, backend endpoints operational, filtering functional, screenshot walkthrough |
| Week 3 | Export working, drill-down demo, all views on real data, error handling confirmed |
| Week 4 | Empty states gallery, responsive test results, QA checklist in progress |
| Week 5 | QA complete, staging deployment, known issues log, internal demo recording |

## 8.4 Definition of Done

- Renders correctly with real backend data (not mock)

- Handles empty, loading, and error states

- Responsive on desktop and tablet

- Matches the agreed unified layout pattern

- Reviewed by Diego in a live walkthrough

# 9. Developer-Ready Task Breakdown

## 9.1 Discovery and product definition

| # | Task | Owner | Week |
| --- | --- | --- | --- |
| P1 | Database schema audit: both platforms, all solutions | Dev + Diego | W1 |
| P2 | Classify all planned metrics into Tier A / B / C based on audit | Dev + Diego | W1 |
| P3 | Lock final KPI list for launch | Diego | W1 |
| P4 | Design and document API contract (only for confirmed metrics) | Dev + Diego | W1 |
| P5 | Architecture decision record: standalone app setup | Dev | W1 |
| P6 | Define drill-down panel content per solution | Diego | W2 |
| P7 | Define CSV column structure and filename convention | Diego | W3 |

## 9.2 Backend and data tasks

| # | Task | Week |
| --- | --- | --- |
| BE1 | Audit database schema: tables, fields, date columns, data completeness | W1 |
| BE2 | Identify primary data source (coach vs rolplay.pro vs Rolplay2) | W1 |
| BE3 | Design aggregation query strategy (direct queries vs materialized views) | W1 |
| BE4 | Build aggregation endpoints: Expert Certification (highest priority) | W2 |
| BE5 | Build aggregation endpoints: LMS | W2 |
| BE6 | Build aggregation endpoints: Global Overview | W2 |
| BE7 | Build configuration/assignment endpoints: Master Coach, Simulator, Second Brain | W2 |
| BE8 | Implement date range and comparison period query parameters | W2 |
| BE9 | Build user-level data endpoints (for drill-down panel and table) | W2–W3 |
| BE10 | Multi-tenancy: ensure all queries scope by tenant/org ID | W2 |
| BE11 | Auth endpoint protection and token validation | W1–W3 |
| BE12 | Query performance optimization and database indexing | W4 |
| BE13 | API error response format standardization | W3 |

## 9.3 Frontend: UX and layout

| # | Task | Week |
| --- | --- | --- |
| U1 | Build app shell: sidebar, header, main content area | W1 |
| U2 | Build toolbar: date range, comparison toggle, solution filter | W1–W2 |
| U3 | Empty state messages and illustrations | W4 |
| U4 | Responsive layout testing and adjustments | W4 |
| U5 | Visual polish pass: typography, spacing, colors | W4 |

## 9.4 Frontend: component library

| # | Task | Week |
| --- | --- | --- |
| C1 | SummaryCard (value, label, trend %, sparkline, loading, empty) | W1 |
| C2 | ChartWrapper (title, tooltip, loading, empty, responsive) | W1 |
| C3 | Line chart variant | W1 |
| C4 | Bar chart variant | W2 |
| C5 | Stacked bar chart variant | W2 |
| C6 | Area chart variant | W2 |
| C7 | DataTable (sortable, searchable, paginated, row click) | W2 |
| C8 | UserDetailPanel (slide-over) | W3 |
| C9 | SkeletonLoader (card, chart, table) | W1 |
| C10 | ErrorState component with retry | W3–W4 |

## 9.5 Filtering and date logic

| # | Task | Week |
| --- | --- | --- |
| F1 | Date range selector: presets (7d, 30d, 90d) + custom picker | W2 |
| F2 | Comparison period auto-calculation | W2 |
| F3 | Solution multi-select filter | W2 |
| F4 | Filter state management (URL params for shareability) | W2 |
| F5 | Filter-to-API query parameter mapping | W2 |

## 9.6 Charts per view

| # | Task | Week |
| --- | --- | --- |
| R1 | Recharts integration and theme setup | W1 |
| R2 | Global: certifications over time line chart | W2 |
| R3 | LMS: module completions over time line chart | W2 |
| R4 | Coach: use case deployment bar chart | W2 |
| R5 | Simulator: scenario deployment bar chart | W2 |
| R6 | Certification: pass/fail stacked bar chart | W2 |
| R7 | Second Brain: document uploads over time bar chart | W2 |
| R8 | Chart tooltip with current + comparison values | W3 |

## 9.7 Export

| # | Task | Week |
| --- | --- | --- |
| E1 | CSV export function (table data to downloadable file) | W3 |
| E2 | Export respects active filters | W3 |
| E3 | PDF export (Tier 2, if time) | W5 |

## 9.8 QA and validation

| # | Task | Week |
| --- | --- | --- |
| Q1 | Empty state testing: every view, every component | W4 |
| Q2 | Date range edge cases | W4–W5 |
| Q3 | Large dataset performance test | W4–W5 |
| Q4 | Cross-browser (Chrome, Safari, Edge) | W5 |
| Q5 | Tablet responsiveness | W4–W5 |
| Q6 | API error handling (timeout, 500, malformed) | W4 |
| Q7 | CSV export integrity | W5 |
| Q8 | Auth flow end-to-end | W5 |
| Q9 | Multi-tenant data isolation | W5 |

## 9.9 Backlog (Phase 2+)

| # | Item | Blocker |
| --- | --- | --- |
| B1 | User activity tracking infrastructure | Privacy decision |
| B2 | Session-based engagement metrics | B1 |
| B3 | Cross-solution adoption rate | B1 |
| B4 | Master Coach usage analytics | B1 |
| B5 | Second Brain query analytics | B1 |
| B6 | Simulator score trends | B1 |
| B7 | AI-powered insight summaries | Analytics maturity |
| B8 | Custom report builder | Product complexity |
| B9 | Role-based permissions | Product complexity |
| B10 | Scheduled email reports | Infrastructure |

# 10. Open Questions and Confirmed Assumptions

## 10.1 Remaining open questions

| # | Question | Why it matters | When to resolve |
| --- | --- | --- | --- |
| OQ1 | Which platform’s database is the primary data source for v1? (coach, rolplay.pro, or Rolplay2) | Cannot build queries without knowing the target schema | Week 1 |
| OQ2 | What is the exact auth mechanism between the standalone dashboard and existing platforms? | Determines login flow and session handling | Week 1 |
| OQ3 | What database records exist for Simulator sessions? Are session completion records stored? | Determines if practice session count is Tier A or Tier C | Week 1 audit |
| OQ4 | How many users does the largest current client have? | Affects pagination and query performance strategy | Week 1 |
| OQ5 | Is there a deployment pipeline, or must one be created? | Adds time to Week 5 if new | Week 1 |
| OQ6 | Who initiates the privacy policy review for user activity tracking? | Determines Phase 2 timeline for Tier C metrics | Week 2 (decision, not implementation) |
| OQ7 | Should the dashboard align with coach DB schema or Rolplay2 schema? | Affects long-term maintainability | Week 1 |

## 10.2 Confirmed facts (no longer assumptions)

| Item | Confirmed status |
| --- | --- |
| Analytics backend | Does not exist. Must be built from scratch. |
| User activity tracking | Not collected. Privacy policy explicitly says so. Requires policy change before implementation. |
| Dashboard architecture | Standalone application, separate from main platforms. Embeddable when needed. |
| Platform direction | Rolplay2 is the long-term successor to coach. Dashboard should align with this direction. |
| Team | 1 lead developer (backend + frontend), 2 support developers (occasional), Diego as product owner. |
| Timeline | 5 weeks to production-ready first release. |

## 10.3 Working assumptions (still to be validated in Week 1)

- Transactional databases contain user records, module assignments, completion records, quiz scores, and evaluation results with date fields.

- Expert Certification evaluation records include: user ID, score, pass/fail status, evaluation date, certification/module identifier.

- LMS completion records include: user ID, module ID, completion date, quiz score (if applicable).

- Multi-tenancy is implementable by filtering on an organization/tenant ID field in the database.

- The existing auth system can issue tokens that the standalone dashboard can validate.

- Data volumes are manageable with direct SQL aggregation (no need for a separate analytics warehouse for v1).

# Appendix A — Design Reference Notes

Visual benchmark: Shopify Analytics (referenced in project screenshots). Key patterns:

- Summary cards with sparklines and trend indicators at top

- Clean date range + comparison selectors in toolbar

- Primary chart with tooltip showing current vs. comparison values

- Muted palette with green (positive) and red (negative) for deltas

Current state: The existing Rolplay admin panel is a PHP-based operational tool with no analytics, charts, KPIs, or filtering. The new dashboard replaces this for the analytics use case.

Important note on visual density: Because some solution views (Master Coach, Simulator, Second Brain) will have fewer metrics at launch due to Tier C data limitations, those views may feel sparse. This is acceptable for v1 — the layout structure should still follow the unified pattern (cards + chart + table) even if the card count is lower. The visual consistency matters more than filling every slot with metrics.

# Appendix B — Component Inventory

| Component | Variants | Reused across |
| --- | --- | --- |
| SummaryCard | Default, loading, empty, alert | All views |
| ChartWrapper | With/without comparison overlay | All views |
| LineChart | Single line | Global, LMS |
| BarChart | Simple, stacked | Coach, Simulator, Cert, Second Brain |
| AreaChart | Simple | Enhancement only (Phase 2) |
| DataTable | Sortable, searchable, paginated, row click | All views |
| UserDetailPanel | Slide-over | All views |
| DateRangePicker | Presets + custom | Toolbar |
| SolutionFilter | Multi-select chips | Global Overview |
| SkeletonLoader | Card, chart, table variants | All components |
| EmptyState | Per-view messaging | All views |
| ErrorState | Retry action | All data-dependent components |
| ExportButton | CSV (Phase 1), PDF (Phase 2) | Table views |
| TrendIndicator | Up (green), down (red), neutral | Summary cards |
| Sparkline | Mini line (no axis) | Summary cards |

# Appendix C — Phase 2 Prerequisites

The following items must be completed before Phase 2 (activity-based analytics) can begin:

| # | Prerequisite | Notes |
| --- | --- | --- |
| 1 | Privacy policy review and update | Legal must approve language permitting user activity data collection. This may require user consent mechanisms. |
| 2 | Activity tracking architecture design | Decide: event-based (each interaction logged), session-based (start/end only), or hybrid. Consider data storage, retention, and volume. |
| 3 | Tracking implementation across 5 solutions | Each solution needs instrumentation to emit activity events. Scope and effort depend on architecture decision. |
| 4 | Analytics database or data pipeline | If activity volume is high, direct SQL aggregation may not be sufficient. May need a lightweight event store or scheduled aggregation jobs. |
| 5 | Phase 2 KPI finalization | Once data is flowing, confirm which Tier C metrics to promote to production. |

Recommendation Initiate the privacy policy review in parallel with Phase 1 development. This is a non-engineering dependency that can take weeks to resolve. Starting early ensures Phase 2 is not blocked by a policy approval backlog.

End of document. Ready for developer kickoff meeting.