## Pro Journey Tracker
Journey ID | Ticket Title | Epic | Priority | Status | Assigned To | Sprint | Start Date | Target Date | Actual Completion Date | Notes
J1 | Database Schema Audit | Backend | Must | Pending | You | Sprint 1
J2 | Identify Available Tables & Fields | Backend | Must | Pending | You | Sprint 1
J3 | KPI Mapping with Data | Analytics | Must | Pending | You | Sprint 1
J4 | Define Missing Data | Analytics | Must | Pending | You | Sprint 1
J5 | Design API Contract | Backend | Must | Pending | You | Sprint 1
J6 | Setup Next.js App | Frontend | Must | Pending | You | Sprint 1
J7 | Build Certification API | Backend | Must | Pending | You | Sprint 2
J8 | Build LMS API | Backend | Must | Pending | You | Sprint 2
J9 | Build Global Metrics API | Backend | Must | Pending | You | Sprint 2
J10 | Create Dashboard Layout | Frontend | Must | Pending | You | Sprint 2
J11 | Implement Filters | Frontend | Must | Pending | You | Sprint 2
J12 | Implement Charts | Frontend | Should | Pending | You | Sprint 2
J13 | Connect APIs to Frontend | Full Stack | Must | Pending | You | Sprint 3
J14 | Implement Drill-down | Frontend | Should | Pending | You | Sprint 3
J15 | Add CSV Export | Backend | Should | Pending | You | Sprint 3
J16 | Handle Edge Cases | Full Stack | Must | Pending | You | Sprint 3
J17 | Add Empty States | Frontend | Must | Pending | You | Sprint 4
J18 | UI/UX Improvements | Frontend | Should | Pending | You | Sprint 4
J19 | Optimize Queries | Backend | Must | Pending | You | Sprint 4
J20 | Responsive Testing | Frontend | Must | Pending | You | Sprint 4
J21 | Final QA Testing | Testing | Must | Pending | You | Sprint 5
J22 | Fix Bugs | Full Stack | Must | Pending | You | Sprint 5
J23 | Deployment Setup | DevOps | Must | Pending | You | Sprint 5
J24 | Production Launch | DevOps | Must | Pending | You | Sprint 5